## Product No 1 or Sprint No 1
|  | Purpose: | This set of tests is intended to check functionality of the game
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail
1 | 1 | TC.001 | Main Menu Functionality | GUI | 1. Launch Game 2. Click "New Game" Button 3. Click "Help" Button 4. Click "Quit Game" Button | 1. Main Menu is displayed correctly 2. User can move through menu options | The user can see the main menu screen and click on each button to be brought to the correct screen | Each button works with user being able to go to the correct screen | PASS
2 | 1 | TC.002 | Game Action Screen | GUI | 1. Launch Game 2. Click "New Game" Button | 1. Level name displayed at the top of the screen. 2. Player appears in the middle at the bottom of the screen. | The level should be displayed at the top left hand corner of the screen and the player object is at the bottom middle of the screen when the game starts. | Level name is displayed at the top left and player is in the bottom middle of the screen. | PASS
3 | 1 | TC.003 | Game Action Screen | GUI | 1. Launch Game 2. Click "New Game" Button | 1. Background scrolls from top to bottom | The background should scroll from top to bottom when the game starts | Scrolling background starts the the game begins. | PASS
4 | 1 | TC.004 | In Game Menu | GUI | 1. Launch Game 2. Click "New Game" Button. 3. Press "P " Button | 1. In-game menu can be accessed from game. | The player should be able to access the in game while playing the game by pressing the "P" button. | Game is paused and in game menu displays when pressing the "P" button. | PASS
4 | 1 | TC.005 | In Game Menu | GUI | 1. Launch Game 2. Click "New Game" Button. 3. Press "Pause" Button | 1. In-game menu can be accessed from game. | The player should be able to access the in game while playing the game by pressing the "Pause" button. | Game is paused and in game menu displays when pressing the "Pause" button. | PASS
4 | 1 | TC.006 | In Game Menu | GUI | 1. Launch Game 2. Click "New Game" Button. 3. Press either "P" keyboard button or "Pause" Button, 4. All menu options working. | 1. Resume button working. 2. Restart button working. 3. Main Menu button working. | The player should be able to resume or restart the game by clicking on either button. The player should be able to go back to the main menu screen. | Player is able to resume, restart and go back to the main menu screen by clicking on the right buttons. | PASS
5 | 1 | TC.007 | Player Movement | GUI | 1. Launch Game 2. Click "New Game" Button. 3. Use left and right keys to test movement. | 1. Player moves to the left or right | The player should move to the left or the right depending on which key is pressed. | The player can move left and right when pressing the keys. | PASS
5 | 1 | TC.008 | Player Movement | GUI | 1. Launch Game 2. Click "New Game" Button. 3. Tap the bottom of the screen on the left and the right. | 1. Player moves to the left or right | The player should move to the left or the right depending on which side is pressed. | The player can move left and right when on either the left or right side of the bottom corners | PASS
6 | 1 | TC.009 | Player Movement | GUI | 1. Launch Game 2. Click "New Game" Button. 3. Move the player to test screen bounds | 1. Move the player to the left and to the right to the end of each side. | The player should not dissappear of the screen. | The player stays on the screen when it reaches either side | PASS
7 | 1 | TC.010 | Enemy Objects | GUI | 1. Launch Game 2. Click "New Game" Button. | 1. Enemys spawn out of screen and move towards the bottom. | Once the game starts, enemies should fall from the top downwards. | Enemy objects fall from the top of the screen downwards. | PASS
7 | 1 | TC.011 | Remove Enemy Objects | GUI | 1. Launch Game 2. Click "New Game" Button. | 1. Enemies are removed after leaving the screen. | Each enemy object should dissappear after leaving the screen. | Enemy objects are removed when they are gone from screen. | PASS
7 | 1 | TC.012 | Enemy Objects Shoot | GUI | 1. Launch Game 2. Click "New Game" Button. | 1. Second enemy shoots a projectile. | The second enemy should shot a bullet when it enters the screen. | When enemy appears on screen, a bullet is shot. | PASS
8 | 1 | TC.013 | Player Collision | GUI | 1. Launch Game 2. Click "New Game" Button. 3. Allow player to collide with an enemy. | 1. Life is lost when player collides with enemy. | If the user collides with an enemy, the player should lose a life. | Life is lost with a collison between player and enemy. | PASS
9 | 1 | TC.014 | Changing of Levels | GUI | 1. Launch Game 2. Click "New Game" Button. 3. Play game to allow level change. | 1. Level changes after time is up. | After the correct amount of time, the level changes to the correct one. | Levels change successfully after the time for each level is up. | PASS